## Sheet1
THEME | ADVOCACY ISSUE AND RATIONALE | ADVOCACY OBJECTIVE | SUB-OBJECTIVES | ACTIVITIES | MEMBER LEAD | SECTOR PARTNERS / CHAMPIONS | TIMEFRAME | WINDOWS OF OPPORTUNITIES | TARGET STAKEHOLDERS | SUCCESS INDICATORS | MID MILESTONE | MILESTONE | STATUS
WASH Financing | There is dwindling of financial support towards the sector from both government and the donor partners. Most Donors have switched their focus from WASH despite the country still facing huge challenges in the sector. On the other hand government has not committed enough funds to carter for WASH service delivery in districts. | To advocate for increased funding to the WASH sector by undertsanding why most donors have moved out in funding WASH initiatives in the country and gauging why government is not committing for more resources for WASH especially in district councils(O&M). | 1. Donor partners: Give reasons why most have moved out of WASH sector and what can be done to attract other donors | Organize meetings with traditional and non-traditional donors to appeal for more funds in the sector, using evidence | UNICEF, W4P, WaterAid | Lead partner of the Donor Partners Group SWA Task Force | FEBRUARY-DECEMBER 2020 | donor partners meeting and WASH commemoration days | Donor partners(AFDB, World Bank, DFID, EU, UNICEF etc,parliamentary finance committee,Ministry of finance, local government finance committee, | a. Number of donors putting more resources for WASH, and the percent increase it represents | Donors and relevant government government departments buying into our issue & initiate conversations on the issue | Donor partners and government putting in more resources for WASH.
|  |  | 2. Government: Gives proper reasons why there is a lack of serious commitments on financial resources for WASH especially (O&M) for district councils. Map Ways on how this could rectified with support from ministry of finance and other relevant government departments | Engage the ministry of finance and parliamentary committee on finance to lobby for increased funding to the sector Develope press releases that outlines financing problems in the sector Engage the MoAIWD and the MLGRD to apply pressure on finance and parliament from within Government | UNICEF, W4P, WaterAid | UNICEF social policy department SWA Task Force Ministry of Local Government and Rural Development Management and Governance TWG | FEBRUARY-APRIL 2020 | Parliamentary sitting, MLGRD budget consultations |  | b. Percent increase in funding for WASH from central government to local authorities that is for operations (eg. Not just salaries devolved) | Donors and relevant government government departments buying into our issue & initiate conversations on the issue
WASH Systems Strengthening | Limited awareness on SWA partnership & linkage to in-country processes. Historically SWA has never been (fully) aligned to WASH sector processes. Most sector processes run parallel to SWA collaborative behaviors. Additionally, there is inadequate commitment from government and Donor partners to Fulfill SWA agreements. Malawi is a party to SWA conventions, most notably joint financing agreements as well as WASH sector national budget increments. But, there is less commitment by donors and government to fulfill the agreements | A. To ensure improved awareness and integration of SWA agenda within existing WASH structures & processes. B. To strengthen accountability of donor partners, WASH stake holders and government to fulfill SWA commitments. | 1. Initiate conversations that will catalyze action on SWA building blocks & country commitments??? & collaborative behaviors by taking advantage of already existing WASH forums and making presentations on SWA agenda and conduct buy in meetings with WASH private actors | Come up with a WASH corner in print media and use the WASH media forum to write articles that explain SWA collaborative behaviors and its linkage to WASH programming, present on SWA collaborative behaviors in various sector meetings and regional chapters and hold interface meetings with well drillers, pit emptiers, pure water manufacturers and water boards by explaining how SWA collaborative behaviours link to their daily work | WASH Media forum, Wesnet secretariat, WaterAid | Champion: Director of Water supply and sanitation services | FEBRUARY 2020-FEBRUARY 2021 |  | Planning department under MOAIWD, SWA taskforce | Number of SWA KPI reported against during JSR/Sector performance Reviews.Number of WASH actors integrating SWA collaborative behaviours in their work.Number of private actors joining the SWA taskforce | WASH stakeholders seeking more clarification on SWA building blocks and their allignment to WASH programming. Planning department seeking interest to know more on how SWA building blocks could be incoporated in JSR reporting tools. | Planning department under MOAIWD continue to incorporate SWA building blocks & collaborative behaviors in JSR reporting frame.WASH stakeholders begin to integrate SWA collaborative behaviors in their work.Private actors join the SWA taskforce and begin to integrate most of SWA collaborative behaviors in their work.
|  |  | 2. To strengthen accountability of donor partners, WASH stake holders and government to fulfill SWA commitment.To lobby the reduction of vacancy rates of WASH positions at district level especially WMAs | Continue Engaging the SWA taskforce to make follow up meetings with key stakeholders like DPs and governments on SWA agreements.To continue Engaging the Director of human resources under MOIAWD to check on progress for recruitment of critical staff in district councils.To lobby for the finalization of a joint financing agreement by facilitating a meeting between donors and government | Secretariat, any volunteer member | SWA Taskforce Management and governance TWG | FEBRUARY 2020-FEBRUARY 2021 | Sector working group meetings, DPs meetings | Director of Human resource, Local government finance committee | Number of SWA commitments integrated into national government and Donor partners working processes.Numbner of districts rcruiting critical staff | Government and Dps agree on the terms on which the JFA could be implemented. District councils begin to advertise for WASH personel to fill vacancies at district level | DPs and WASH actors share with WESNet annual budgets for government consolidation of a sector budget.District councils recruit critical staff.
WASH Policy | Outdated WASH policies that have not incorporated the SDG 6. Most WASH policies are outdated and there have been no significant progress to facilitate their review. Most of these policies have not integrated the SDG 6 indicators in their frameworks. Where policies and guidelines are up-to-date, member organisations do not always know about them or follow them. | To continue facilitating the effective engagement of non-state actors in the review of the current WASH policies in line with SDG 6 prior to the review of sanitation policy and water policy | 1. Develop a guideline for engaging CSOs to identify gaps with the 2005 Water policy and develop a policy brief.Disseminate the developed sanitation policy brief and water policy brief to relevant stakeholders to promote awareness of policy gaps identified that need to be rectified. | WASH CSOs input on national sanitation and Water policy consolidated into policy briefs and the briefs disseminated to relevant stakeholders for a possible government adoption. | Policy review taskforce | UNICEF Social policy dept | FEBRUARY - APRIL 2020 | WASH policy review processes.Regional chapters | Planning department under MOAIWD, Consultant | Input levels of Non-state actors taken on board into the policies | Wesnet members and donors buying into policy requests submitted by WESNET secretariat | Wesnet's input to the reviews successfully adopted and reflected in the new policies
|  |  | 2. Engaging members on understanding National Policies and Guidelines and how they apply to them | Workshop on orienting members on common infractions and adherence to government regulations. Ongoing reminders and messages to members. | Secretariat(Any volunteer member) | Various relevant Ministry departments | FEBRUARY 2020- Workshop FEBRUARY 2020 - FEBRUARY 2021 - Ongoing
Menstrual Hygiene Management | Access to absorbent materials is low due to high prices in the current tax regime.Menstrual products are a basic need that should be tax exempt of import duty and VAT. | To call for a revised tax regulations; through a removal of VAT and import duty. | Menstrual Health Day: high level public event. Should have a longer timeframe. Have lobbying activities with women caucus, female MP's. We need to involve the media; articles, statements and we could attend talkshows. Position paper- key messaging. (Tinveni Radio) (Chanco TV) - Engagement meetings | To develop an issues paper and publish in print media. Use the issues paper to debrief influential figures. Engage the media on MHM affordability and accessibility issues. | MHM Taskforce(Any volunteer member) | MHEN, MJEN, GCNET, GENET,UNICEF social policy department Champions: First lady, speak of parliament, TA Kachindmoto, 'first deputy speaker', George Jobe (Malawi Health Equity Network), Lucias Banda |  | Menstrual Health Day 26 May - Parliamentary Committee Meetings - Women Cauces Meetings - International Day of the Girl Child June - International Women's Day - Mothersday - Human Rights Day | Ministry of finance, MRA | Issues paper developed, number of engagement meetings with politicians and the media | Bill on tax exemption on sanitary pads tabled in parliament | TAX on sanitary pads exempted
Sanitation and Hygiene | The National Sanitation and Hygiene Technical committee only meets diuring preparations for global sanitation and hygiene commemoration days. The TORs for the NSHTC have not yet developed despite the committee operating under a new strategy. The ODF status of the country is not yet well known as the the NSHTC has not been neeting to check on country progress. There is therefore the need that the NSHTC develop TORs which are alligned to the new strategy and as well meets regulary to check on the country progress towards realisation of 100 percent latilinisation and handwashing with soap. Despite the NSH strategy being signed, there has been no dissemination meetings with critical staff at district level to promote the strategy | To ensure the NSHTC revises & adopts TORs (to match with new strategy); draws up a calendar of events/action/operational plan & conducts meetings regularly. To strategise on assisting the NSHTC with dissemination meetings | Organise meetings where the NSHTC gives an update on country ODF status (& strategies towards maintaining the status?), organise strategy dissemination meetings with crucial district stakeholders, engage the NSHTC to review its TORs | To engage the NSHTC to review its TORs, continual update of ODF country status and disseminate the National sanitation and hygiene strategy | Secretariat | UNICEF, USAID,AFDB |  | Sanitation policy review meetings, Global commemoration days on sanitation and hygiene | NSCHU and NSHS | Number of NSHTC meetings in a year,number districts aware of the NSH contents, | ODF slippage rates given regulary. 5 district have had dissemination workshops on NSHS. Wes members commenting on Revised TORs for the NSHTC | TORs for the NSHTC developed & approved/adopted, country status on ODF given regulary & strategies/commitments drawn towards maintaining ODF status and the NSHS disseminated to atleast 10 districts
Water Resource Management and Climate Resiliency | In the face of dwindling water resources, Malawi can no longer afford to pollute and misuse her water and water catchments with little to no regulation. Since the Water Resources Act of 2013, little headway has been made in fully operationalising the NWRA or in understanding how various stakehlders will be held accountable to regulations. Existing regulations have barely been enforced to date. | To engage the newly formed NWRA, MEPA, and other relevant stakeholders to bolster water resources regulation and to find ways to hold NGOs and private sector accountable. Also to engage with membership on increasing awareness of climate resiliency andand Water demand management catchment protection in implementation of WASH activities. | 1. Engage with regulators such as NWRA and MEPA to push for public accountability of the regulatory process, and to understand how CSOs may be engaged and/or subjected to different aspects of regulation. | Push for public statements from NWRA and MEPA about the progress on their operationalisation and key milestones or reasons for the delay. CO-develop ways that CSOs may be part of the regulatory process and accountability structures. | BASEFLOW, World vision, United Purpose, CCODE, Habitat | NWRA / MEPA Water Resources TWG WASAMA CISANET | April 2020-April 2021 | WASH Commemoration days, Sector meetings,policy review meetings | NWRA;MEPA, WATERBOARDS | 1.Number of meetings between NGOs and regulatory authorities on catchment protection awareness.2.Number of NGOs actively involved in the catchment protection regulatory mechanisms. | Mid milestones-NWRA and MEPA starting to take WASH actors into accountable in issues of Water resources. 50 Percent of WESNET members aware of the regulatory mechanisms that exist for catchment protection | Fully functional NWRA AND MEPA.All WASH NGOs fully aware of the regualtrory mechanisms that exist for catchment protection
|  |  | 2. Engage memebership on existing regulatory frameworks and their associated responsibilities, as well as in sharing best practices for integrating catchment protection, water resources, and climate resiliency into WASH projects | Understand regulatory obligations of NGOs as defined by regulatory bodies such as NWRA/MEPA and invite them to orient the membership, or to co-design and produce relevant media to educate organisations on their responsibilities. Identify organisations and academics that have good practices to share with others, and advocate through knowledge sharing (work with RKE TWG) | Water missions, Baseflow, CICOD, Habitat for Humaniuty | NWRA / MEPA RKE TWG |  | WASH Commemoration days, Sector meetings,policy review meetings